## Draft - 29Mar2017
Timeline/Process for next update of Projections in 2019
| 2018 | [11 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021
WorkStream | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June
LPT Planning / District Planning
Census update
UoW - Population projections
ME - Economic projections
WISE - version update
Draft Projections - using 2018 population data, but 2013 household generation rates
WISE V1.5 Update
Complete
2018
Census
2021 LTP's Complete
Date/timing Know
Timing to be confirmed/decided
2017 Wraps aerial images
Updated TA population projections
Census results - population
FINAL - Projections data - Population, households, labourforce, employment, Added Value.
Regional economic data update
Updated WOW Population file
Census results - household generation rates
Updated Zoning Layers/Status
2018 Land Use layer
Current District Plans /Growth Strategy Data
WISE V1.5 Land Use Modelling
Households model - integration and tested
2018 Valuation Database
Land use by TA/CAU/other?
Economic Modelling
Population Modelling
Householdss
2018 LTP's Complete
Other component updates - New Population Model, District Economic Model
DRAFT - Projections data - Population, households, labourforce, employment, Added Value.
WISE V1.5 Land Use Modelling
Re-Run based on 2018 Census Households data
Rating Units?
Dwellings?
Dependent on STATS NZ - delivery dates unknowned
Final Projections - using 2018 population data, household generation rates